## WBS
Tasks | Duration (days) | Precedence | Milestone/Deliverable | Member 1 | Member 2
1.0 Write Project Proposal
1.1 Write Overview, Aim, Obj and Scope | 2 |  |  | 100 | 100
1.2 Derive Project Schedule
1.2.1 Derive WBS | 1 | 1.1 |  | 100 | 100
1.2.2 Derive Gantt | 1 | 1.2.1 |  | 100 | 100
1.3 Gantt Chart |  | 1.2.2 | ✓
1.4 Derive Dev & Demo Platform | 1 | 1.3 |  |  | 100
1.5 Derive Risk Plan | 1 | 1.3 |  | 100
1.6 Project Plan |  | 1.4,1.5 | ✓
2.0 Requirement Specification |  | 1.6
2.1 Derive Functional & Non-Functional Requirements | 2 | 2.0 |  | 100 | 100
2.2 Derive User Stories & Acceptance Criteria | 1 | 2.1
2.2.1 Register & Privacy Setting | 1 | 2.2 |  | 100
2.2.2 Manage Food Inventory | 1 | 2.2.1 |  |  | 100
2.2.3 Donation Posting/Claiming | 1 | 2.2.2 |  | 100
2.2.4 Analytics & Meal Plan | 1 | 2.2.3 |  |  | 100
3.0 Design Specification | 1 | 2.2.4
3.1 Architectural design (deployment diagram) | 1 | 3.0 |  | 100
3.2 High-level components (frontend, backend, DB) | 1 | 3.1 |  |  | 100
3.3 ERD (conceptual) | 1 | 3.2 |  | 100
3.4 Site map | 1 | 3.2 |  |  | 100
3.5 Wireframes (Login, Dashboard, Inventory, Donations, Analytics, Meal Plan) | 1 | 3.4 |  | 100 | 100
3.6 Data dictionary | 1 | 3.3,3.5 |  | 100
4.0 Project Schedule Artefacts |  | 3.6
4.1 WBS Figure (Figure 1) | 1 | 4.0 |  | 100
4.2 Milestones & Deliverables Figure (Figure 2) | 1 | 4.1 |  |  | 100
4.3 Gantt with Baseline & Resources (Figure 3) | 1 | 4.2 | ✓ | 100 | 100
5.0 Technical Environment |  | 4.3
5.1 Development Platform (IDE, tools, versions) | 1 | 5.0 |  |  | 100
5.2 Demonstration Platform (browser/OS/localhost) | 1 | 5.0 |  | 100
6.0 Risk Management |  | 5.2
6.1 Identify & assess risks | 1 | 6.0 |  | 100
6.2 Mitigation & contingency planning | 1 | 6.1 |  |  | 100
7.0 Final Submission |  | 6.2
7.1 Document compilation & proofreading | 1 | 7.0 |  | 100 | 100
7.2 References & formatting | 1 | 7.1 |  | 100 | 100
7.3 Final submission to LMS |  | 7.2 | ✓

## Members
Member Column | Name
Member 1 | Bin Hangyu (Leader)
Member 2 | Zhang Wenzhe (Member)